## Sheet1
Name-Surname: Djeneba DIALLO Student number: 220513675 Role: Developer
Project automation system for students and teachers
Studex Gantt Chart (May 2024 - June 2024)
Task | Start Date | End Date | Duration (Days)
1. Project Kickoff | 2024-05-01 | 2024-05-07 | 7
2. Requirements Gathering | 2024-05-08 | 2024-05-25 | 16
3. Design Database Schema | 2024-05-25 | 2024-06-04 | 10
4. Develop Front-end Interface | 2024-06-04 | 2024-06-30 | 27
5. Implement Back-end Functionality | 2024-06-21 | 2024-07-05 | 15
6. Integration and Testing | 2024-07-05 | 2024-07-15 | 11
7. User Authentication | 2024-07-16 | 2024-07-29 | 14
8. Documentation | 2024-07-30 | 2024-08-12 | 14
9. Deployment Preparation | 2024-08-13 | 2024-08-22 | 10
10. Project Review and Closure | 2024-08-22 | 2024-08-29 | 8